# Glasgow City Council Education Services

# Improvement Planning

| Establishment | Rowan Tree Nursery | Session | 2013-2014 |
| --- | --- | --- | --- |

CONTENTS

1.	Vision, Values and Aims

2.	Summary of Self Evaluation Process

3.	Overview of 3-year Planning Cycle

4.	Priorities for Improvement in the current year

- Action planning

- Appendices:

  - Action Plan Summary for Stakeholders

  - Monitoring of Progress of Improvement Plan

Signatures:

| Head of Establishment | Pamela Ewart | Date | 28/05/2013 |
| --- | --- | --- | --- |

| Quality Improvement Officer |  | Date |  |
| --- | --- | --- | --- |

| Area Education Manager |  | Date |  |
| --- | --- | --- | --- |

1a Our vision, values and aims

Our vision, values and aims Our vision is to provide a service of the highest quality in partnership with Parents/Carers, children, staff and the wider community. We are committed to the development of independent learners who have high self esteem, self confidence, empathy and care for others. WE AIM TO; To provide children with valuable experiences to develop confidence, independence, resilience and an enthusiasm to learn To provide quality care based on inclusion to foster a trusting and communicative relationship between children, parents and staff To work in partnership with parents, relevant agencies and the wider community to ensure children have access to the support required in order for them to reach their full potential To continue to develop ourselves professionally so that we can provide a high quality service for all our service users To provide opportunities for learning through play offering a broad and balanced curriculum, creating a positive atmosphere where children are individually supported and/or challenged To create appropriate opportunities for development of early Literacy, Numeracy and Health and Wellbeing

1b How our vision, values and aims were developed and how our stakeholders were consulted

Parent continuous feedback, questionnaires and audits of self evaluation Parent settling in evaluations and exit interviews Steering group meeting Children’s questionnaire and consultation Staff meetings, questionnaires, audits and PDP’s Website and facebook

Summary of self evaluation process

How we carried out our self-evaluation and involved our stakeholders

The Glasgow City Council monitoring documents and CATC have been utilised to determine appropriate questionnaires and audits for stakeholders and staff. These are complete twice annually; however on-going self evaluation is timetabled and complete on a term time basis. We have included the Journey to excellence reflective questioning to challenge the thinking behind the monitoring of the service for staff. Quality Indicators have also assisted in determining a key focus for improvement with tasks and personal development targets assigned to all staff. The Parent Steering group have been consulted on all aspects of improvement for the nursery and in the compilation of reports and policies. These consultation and communication methods have changed over time to include e-mailing information and surveys to support improvement. BA training has highlighted some elements of improvements to further develop children’s thinking and learning.

| Quality Framework | Our key strengths | Our areas for improvement |
| --- | --- | --- |
| Successes and achievements | 2.2 Strong parent committee Very Good attendance at parental involvement events such as Parents Day, Grandparents Day, World Book Day, 5K Fun Run, Charity Race Night, Open Day, Graduation, Xmas Show Good parent feedback from parent events Parental involvement in nursery decisions Parental Involvement in policy reviews Good use of Home Links and feedback | 4.1 Work more closely with the local community Use local community to improve experiences for children |
| Work and life of school/centre | 5.3 Improved outdoor opportunities and experiences “We are going on a bear hunt” outdoor adventure video New outdoor resources New numeracy resources Children choose and reviewed resources Improved numeracy skills and knowledge Staff confidence increased through outdoors (Literacy, numeracy & HWB) New up to date additional support paperwork in place | 5.1 Improve transitions from room to room 5.4 Improve manageability of assessment approaches and the recording of assessment information 7.1 Improve recruitment of staff - Application form to include details of skills and knowledge Improve induction process to be more in depth and relevant to post |
| Vision and leadership | 9.3 Staff monitoring groups Leadership areas Improved motivation Improved commitment Distributed leadership present and effective Good team work and partnership working Good levels of consultation between staff and management | 9.4 Leaders to continue to improve leadership skills |

3. Overview of three-year planning cycle

| Quality framework | QI | Year 1 priority |  | QI | Year 2 priority |  | QI | Year 3 priority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Successes and achievements | 4.1 | Improve the extent to which the centre engages with the local community. |  | 1.1 |  |  | 3.1 |  |
| Work and life of the school/centre Work and life of the school/centre | 5.4 | Improve assessment approaches including arrangements for recording and reporting. Use assessment information to identify and plan future learning. |  | 5.1 | Improve Transitions |  |  |  |
|  | 7.1 | Improve recruitment, appointment and induction of staff. |  |  |  |  |  |  |
| Vision and leadership | 9.4 | Leaders to make continuous improvement. |  |  |  |  |  |  |

| 4. Priorities for improvement in the current year |  | Year | 1 |
| --- | --- | --- | --- |

|  | Priority | Main driver of priority: |  | Alignment with: |
| --- | --- | --- | --- | --- |
| No. |  | Self- evaluation | Authority Quality Review | HMIe report |  | QI | National Priority | Learning Community Priority | Local Improvement Plan | Single Outcome Agreement |
| 1. | Improve the extent to which the centre engages with the local community and promotes community learning | X |  |  |  | 4.1 | X |  |  |  |
| 2. | Improve assessment approaches including arrangements for recording and reporting. Use assessment information to identify and plan future learning. | X | X |  |  | 5.4 | X |  |  |  |
| 3. | Improve recruitment, appointment and induction of staff. | X |  |  |  | 7.1 | X |  |  |  |
| 4. | Leaders to make continuous improvement. | X |  |  |  | 9.4 | X |  |  |  |

| Priority No. | QI | Priority | Expected outcomes for learners which are measurable or observable |
| --- | --- | --- | --- |
| 1 | 4.1 | Improve the extent to which the centre engages with the local community and promotes community learning | Members of the local community will be actively involved with the nursery. We will have effective partnership arrangements which enrich our provision and the experiences of our children. |

5. Action Planning

| Tasks to achieve priority | Timescale | Person responsible | Resources and staff development | Monitoring progress and evaluating impact |
| --- | --- | --- | --- | --- |
| Audit current involvement with the local community | Aug 2013 | Mary/Gemma/ Amy | Previous evidence folder Photo Albums | Staff and parents meeting to discuss previous community involvement and learning. Minutes of meeting. |
| Consult with parents, children and the local community about what sort of community involvement they would like to be involved in Make calendar of events incorporating local links | Sept 2013 | Shannen/ Veronica/ Cassie | Questionnaires Minutes of Meetings Newsletters Facebook Calendar of events | Meetings to discuss feedback from questionnaires. |
| Staff in house training on promoting community links and ideas for involvement | Oct 2013 | Pamela | Training Tracker Training Powerpoint Training Evaluations Etwinning | Staff training evaluations about who staff think they can involve the community in our nursery and how children and families will benefit. |
| Implement community links Visit local care homes/library Visit local schools Visit local nurseries | Oct 2013/May 2014 | Mary/Shannen/Cassie | Floorbooks Planning Calendar of events | Evidence folder of action plans, photos, minutes, ideas, suggestions, comments, evaluations etc. |
| Evaluate progress and development | Jun 2014 | All Staff | Wall Displays Questionnaires Minutes of Meetings | Display progress and development through displays. Meetings to discuss progress and evaluate. Give out questionnaires to parents, staff and children. |
| Update relevant policies | July 2014 | Pamela | Staff Meeting (Monitoring/Review Group) | Update Community links and learning policy. |

| Priority No. | QI | Priority | Expected outcomes for learners which are measurable or observable |
| --- | --- | --- | --- |
| 2 | 5.4 | Improve assessment approaches including arrangements for recording and reporting. Use assessment information to identify and plan future learning. | We have manageable arrangements for record keeping which support us to track and record children’s progress and report to parents. Children will contribute information to their own profiles and have a sense of ownership of their own learning. Staff use observations and high quality interaction as assessment approaches. |

| Tasks to achieve priority | Timescale | Person responsible | Resources and staff development | Monitoring progress and evaluating impact |
| --- | --- | --- | --- | --- |
| Audit current assessment approaches and arrangements for recording and reporting | Jul / Aug 2013 | Shauni/Nicola/ Nicolle | Policy folder Previous evidence folder Floorbooks Assessment Folders Profiles/individual plans Lit, Num & HWB Audit | Staff/parents meeting to discuss current assessment approaches and reflect on previous evidence. Minutes of meeting. |
| Consult with parents/staff about what assessment approaches they think are appropriate | Aug/Sept 2013 | Shannen/ Samantha/ Abbey | Questionnaires Minutes of Meeting Visits to other nurseries | Meetings to discuss feedback from questionnaires about current assessment approaches and make decisions about new assessment approaches and possible arrangements for recording and reporting. |
| Plan staff training about assessment Moderation Tasks Blooms Taxonomy (HOTS) | Oct 2013 | Pamela | Training Tracker Training Powerpoint Training Evaluations NAR flow chart HOTS Materials | Staff training evaluations to determine staff new knowledge about assessment approaches and HOTS. |
| Implement changes to assessment approaches Parents info night Trial new planning/profiles Trial new assessment record Peer/self assessments | Oct 2013/May 2014 | Shannen | Individual Plans Profiles Floorbooks Peer/Self Assessments | Parents evaluations about what they gained from assessment info night. Evidence folder of action plans, photos, minutes, ideas, suggestions, comments, evaluations etc. New assessment paperwork |
| Evaluate Progress and development | June 2014 | All Staff | Playroom Monitoring Questionnaires Wall Displays Profiles Individual Plans Floorbooks | Display progress and development. Planning meeting to discuss effectiveness of new assessment methods and HOTS. Minutes of meeting. Give out questionnaires to parents, staff and children. |
| Update relevant policies | July 2014 | Shannen | Staff Meeting (Monitoring/Review Group) | Update Assessment/CFE policy. |

| Priority No. | QI | Priority | Expected outcomes for learners which are measurable or observable |
| --- | --- | --- | --- |
| 3 | 7.1 | Improve recruitment, appointment and induction of staff. | When appointing staff we give due regard to qualifications, skills, knowledge and experience needed for the post. Our induction process will be effective in that staff will gain confidence and knowledge about company policy and procedures prior to starting their post. |
| Tasks to achieve priority | Timescale | Person responsible | Resources and staff development | Monitoring progress and evaluating impact |
| Audit current recruitment and induction procedures | Aug 2013 | Pamela/Shannen | Staff new start packs Current induction paperwork | Staff and parents meetings to discuss current recruitment and induction procedures and paperwork. |
| Consult parents/staff and children about the recruitment procedures | Sept 2013 | Pamela/Shannen | Questionnaires Minutes of Meetings Newsletter | Meetings to discuss feedback from questionnaires and decide on changes needing made to application forms and transitions paperwork. |
| Training on importance of SSSC codes of conduct, national care standards and child at the centre quality indicators | Oct - Nov 2013 | Pamela | Training Tracker Training Powerpoint Training evaluations SSSC codes of conduct NCS and CATC | Staff training evaluations on SSSC, NCS and CATC to see what understanding they have developed as key documents for good practice. |
| Implement changes to recruitment process and induction procedure New application form New induction procedures | Oct 2013/ May 2014 | Pamela/Shannen | New recruitment & induction procedures Playroom Monitoring Support and supervision | Evidence folder of action plans, photos, minutes, ideas, suggestions, comments, evaluations etc New new start paperwork. New Induction paperwork. |
| Evaluate progress and development | June 2014 | All Staff | Questionnaires Monitoring Staff support and supervision Newsletter | Display progress and development through display in staff room and newsletters for parents. Give out questionnaires to parents, staff and children. |
| Update relevant policies | July 2014 | Pamela | Staff Meeting (Monitoring/Review Group) | Update Recruitment & Induction policy and procedures to include changes |

| Priority No. | QI | Priority | Expected outcomes for learners which are measurable or observable |
| --- | --- | --- | --- |
| 4 | 9.4 | Leaders to make continuous improvement. | All staff set high standards of practice, teaching and learning with a focus on impact and outcomes. Staff skills and talents are explored closely and are used to improve the service. Staff are encouraged to take on lead roles in a variety of contexts. |
| Tasks to achieve priority | Timescale | Person responsible | Resources and staff development | Monitoring progress and evaluating impact |
| Audit current leadership practice, staff skills and knowledge | Aug 2013 | Pamela | Policy Folder Evidence folder from previous year Staff CPD folders Bi-Monthly reviews | Staff meeting and individual meetings to discuss staff leadership roles from last year and their achievements. |
| Consult staff about areas of leadership they would like to continue with or change | Sept 2013 | Pamela/Shannen | Questionnaires Minutes of staff meeting Appraisals Support and Supervision | Gather feedback about what areas of leadership they would like to take on this year and put together a new table of leadership areas for staff. |
| Staff training on developing and improving staff skills | Oct - Nov 2013 | Pamela | Training tracker Training PowerPoint Training evaluations Staff development resource books | Staff meeting to decide what training they want to develop their chosen leadership area. Plan and carry out this training to increase staff knowledge and confidence to carry out role.. |
| Implement leadership changes Further define job roles/responsibilities Distributed leadership Student/mentor meetings monthly Monthly senior meetings | Oct 2013/ May 2014 | Pamela/Shannen | Playroom Monitoring Staff CPD folders Bi-Monthly reviews Minutes of meetings | Evidence folder. Individual staff CPD folders. Bi-monthly paperwork to track progress. Minutes of student/mentor meetings Evaluations of senior meetings |
| Evaluate progress and development | June 2014 | All Staff | Questionnaires Appraisals Support and Supervision Evidence of leadership areas in CPD folders | Display staff achievements in staff room for everyone to evaluate their own leadership skills and that of others through self and peer assessment. |
| Update relevant policies | July 2014 | Pamela | Staff meeting (Monitoring/review group) | Update policy on distributed leadership. |

6. Appendices

Appendix a

Action Plan Summary for Stakeholders

| No. | Priority | Expected outcomes for learners which are measurable or observable | Lead responsibility | Timescales |
| --- | --- | --- | --- | --- |
| 1 | Improve the extent to which the centre engages with the local community. | Members of the local community will be actively involved with the nursery. We will have effective partnership arrangements which enrich our provision and the experiences of our children. | Mary/Cassie | Aug 13- July 14 |
| 2 | Improve assessment approaches including arrangements for recording and reporting. Use assessment information to identify and plan future learning. | We have manageable arrangements for record keeping which support us to track and record children’s progress and report to parents. Children will contribute information to their own profiles and have a sense of ownership of their own learning. Staff use observations and high quality interaction as assessment approaches. | Shannen | Aug 13- July 14 |
| 3 | Improve recruitment, appointment and induction of staff. | When appointing staff we give due regard to qualifications, skills, knowledge and experience needed for the post. Our induction process will be effective in that staff will gain confidence and knowledge about company policy and procedures prior to starting their post. | Pamela | Aug 13- July 14 |
| 4 | Leaders to make continuous improvement. | All staff set high standards of practice, teaching and learning with a focus on impact and outcomes. Staff skills and talents are explored closely and are used to improve the service. Staff are encouraged to take on lead roles in a variety of contexts. | Pamela | Aug 13- July 14 |

6. Appendices

Appendix

Monitoring of Progress and Evaluating the Impact of the Improvement Plan

| Priority No. |  |  | Progress check 1 Date: |  | Progress check 2 Date: |  | Progress check 3 Date: |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Task | Timescale | Comment on progress |  | Comment on progress |  | Comment on progress |
| 1 | Audit current involvement with the local community | Aug 2013 |  |  |  |  |  |
|  | Consult with parents, children and the local community about what sort of community involvement they would like to be involved in | Sept 2013 |  |  |  |  |  |
|  | Staff in house training on promoting community links and ideas for involvement | Oct 2013 |  |  |  |  |  |
|  | Implement community links | Oct 2013/May 2014 |  |  |  |  |  |
|  | Evaluate progress and development | Jun 2014 |  |  |  |  |  |
|  | Update relevant policies | July 2014 |  |  |  |  |  |
| 2 | Audit current assessment approaches and arrangements for recording and reporting | Jul / Aug 2013 |  |  |  |  |  |
|  | Consult with parents/staff about what assessment approaches they think are appropriate | Aug/Sept 2013 |  |  |  |  |  |
|  | Plan staff training | Oct 2013 |  |  |  |  |  |
|  | Implement changes to assessment approaches | Oct 2013/May 2014 |  |  |  |  |  |
|  | Evaluate Progress and development | June 2014 |  |  |  |  |  |
|  | Update relevant policies | July 2014 |  |  |  |  |  |
| 3 | Audit current recruitment and induction procedures | Aug 2013 |  |  |  |  |  |
|  | Consult parents/staff and children about the recruitment procedures | Sept 2013 |  |  |  |  |  |
|  | Training on importance of SSSC codes of conduct, national care standards and child at the centre quality indicators | Oct - Nov 2013 |  |  |  |  |  |
|  | Implement changes to recruitment process and induction procedure | Oct 2013/ May 2014 |  |  |  |  |  |
|  | Evaluate progress and development | June 2014 |  |  |  |  |  |
|  | Update relevant policies | July 2014 |  |  |  |  |  |
| 4 | Audit current leadership practice, staff skills and knowledge | Aug 2013 |  |  |  |  |  |
|  | Consult staff about areas of leadership they would like to continue with or change | Sept 2013 |  |  |  |  |  |
|  | Staff training on developing and improving staff skills | Oct - Nov 2013 |  |  |  |  |  |
|  | Implement leadership changes | Oct 2013/ May 2014 |  |  |  |  |  |
|  | Evaluate progress and development | June 2014 |  |  |  |  |  |
|  | Update relevant policies | July 2014 |  |  |  |  |  |